## Sheet1
No | Opening Balance Data | Streams | PIC | Cut Off Date | Handover | Note | Confirm | Upload
[5 empty] | date (NP to ME) |  | Data
1 | PR & PO RM , PM | PTP | Rini | 2014-03-28 | 2014-03-30 |  | 100% | 100%
2 | PR & PO Sparepart & Others | PTP | Rini | ` | 2014-03-30 |  | 100% | 100%
3 | On hand & all Inventory (raw material, wip,finish good) and Sparepart | PTP | Titin | 2014-03-28 | 2014-03-30 |  | 100% | 100%
4 | Invoice Payables (invoice + payment) | PTP | Silvi | 2014-03-28 | 2014-03-30 |  | 100% | 100%
5 | Prepayment | PTP | Silvi | 2014-03-28 | 2014-03-30 |  | 100% | 100%
6 | Sales Order | OTC | Dine & Pipit | 2014-03-28 | 2014-03-30 |  | 100% | 100%
7 | Invoice Receivables (invoice) | OTC | Lusi | 2014-03-28 | 2014-03-30 |  | 100% | 100%
8 | AR Receipt (unapply receipt) | OTC | Lusi | 2014-03-28 | 2014-03-30 |  | 100% | 100%
9 | Production batch | OPM | Nia | 2014-03-28 | 2014-03-30 |  | 100% | 100%
10 | Item Cost – Production | OPM | Christine | 2014-04-05 |  | bu christine | 0%
11 | Fixed Asset | FIN | Noviliana | 2014-04-05 |  | bu novi | 0%
12 | Budget | FIN | Noviliana | 2014-04-05 |  | bu novi | 0%
13 | Trial Balance | FIN | Noviliana | 2014-04-05 |  | bu novi | 0%
Total