## Master
[10 empty] | Collection |  | Cleansing |  | Upload
Seg | Stream | Module | Data Name | Type | Upload Method | Pre-require Setup | Template | Note | PIC | Trimas % | DL | Trimas % | DL | Trimas % | DL
1 | PTP | PO | Job | Master | Manual | - | Y |  | Rini | 100% |  | 100% |  | 100%
2 | PTP | PO | Position | Master | Manual | 1. Job | Y |  | Rini | 100% |  | 100% |  | 100%
3 | PTP | PO | Personnel/Employee (PO, WMS) | Master | Manual | 1. Job 2. Position | Y |  | Rini | 100% |  | 100% |  | 100%
4 | PTP | PO | Position Hierarchy (approval path) | Master | Manual |  | Y |  | Rini | 100% |  | 100% |  | 100%
5 | PTP | PO | Approval Group & Approval Assignment | Master | Manual |  | Y |  | Rini | 100% |  | 100% |  | 100%
6 | PTP | PO | Suppliers Purchasing (Internal & External) |  | Interface |  |  |  | Rini | 100% |  | 100% |  | 100%
7 | PTP | AP | Suppliers Payables (Internal & External) | Master | Interface | 1. COA Liability & Prepayment 2. Payment Terms | Y | blm dpt dr bu novi | Novi | 0% |  | 0% |  | 0%
8 | PTP | AP | Payment Terms | Master | Manual |  | Y |  | Rini | 100% |  | 100% |  | 100%
9 | PTP | AP | Withholding Tax | Master |  |  | Y |  | Feny | 100% |  | 100% |  | 100%
10 | PTP | AP | Document Sequence (AP Invoice & Payment) | Master |  |  | Y |  | Novi | 100% |  | 100% |  | 100%
11 | PTP | INV | Unit of Measures | Master | Data loader |  | Y |  | Santi | 100% |  | 100% |  | 100%
12 | PTP | INV | Item UOM Conversion | Master | Data loader |  | Y |  | Santi | 100% |  | 100% |  | 100%
15 | PTP | INV | Item Category - Sales Categories | Master | Data loader |  | Y |  | Novi, Rini | 100% |  | 100% |  | 100%
15 | PTP | INV | Item Category - Purchasing Categories | Master | Data loader |  | Y |  | Novi, Rini | 100% |  | 100% |  | 100%
17 | PTP | INV | Item Category - Product Category | Master | Data loader |  | Y |  | Novi, Cristine | 100% |  | 100% |  | 100%
18 | PTP | INV | Item Category - Cost Component Class | Master | Data loader |  | Y |  | Novi, Cristine | 100% |  | 100% |  | 100%
19 | PTP | INV | Item Category - GL Class | Master | Data loader |  | Y |  | Novi, Cristine | 100% |  | 100% |  | 100%
20 | PTP | INV | Item Category - INV | Master | Data loader |  | Y |  | Novi, Titin | 100% |  | 100% |  | 100%
22 | PTP | INV | Item Category - Planning Category | Master | Data loader |  | Y |  | Novi, Santi | 100% |  | 100% |  | 100%
23 | PTP | INV | Item Master - Raw Material | Master | Interface | 1. UOM 2. Item Category 3. | Y |  | Santi | 100% |  | 100% |  | 100%
24 | PTP | INV | Item Master - Work In Process | Master | Interface | idem | Y |  | Santi | 100% |  | 100% |  | 100%
25 | PTP | INV | Item Master - Finished Goods | Master | Interface | idem | Y |  | Santi | 100% |  | 100% |  | 100%
26 | PTP | INV | Item Master - Reject | Master | Interface | idem | Y |  | Santi | 100% |  | 100% |  | 100%
27 | PTP | INV | Item Master - Spareparts | Master | Interface | idem | Y |  | Titin | 100% |  | 100% |  | 100%
28 | PTP | INV | Item Master - Expense | Master | Interface | idem | Y |  | Novi | 100% |  | 100% |  | 100%
29 | PTP | INV | Item Master - Asset | Master | Interface | idem | Y |  | Novi | 100% |  | 100% |  | 100%
30 | OPM | CM | Cost Component Class | Master | Manual |  | Y |  | Christine | 100% |  | 100% |  | 100%
31 | OPM | CM | Cost Analysis Code | Master | Manual |  | Y |  | Christine | 100% |  | 100% |  | 100%
32 | OPM | PE | Resource Class | Master | Manual |  | Y |  | Ujang | 100% |  | 100% |  | 100%
33 | OPM | PE | Generic Resource | Master | Interface | 1. Resource Class 2. Cost Component Class | Y |  | Ujang | 100% |  | 100% |  | 100%
34 | OPM | PE | Plant Resource | Master | Interface | 1. Generic Resource 2. Calendar (Inventory) 3. Equipment Item (EAM) 4. UOM 5. UOM Conversion 6. Organization Code *Note: Linking Equipment Item-Plant Resources | Y |  | Ujang | 100% |  | 100% |  | 100%
35 | OPM | PE | Activity | Master | Manual |  | Y |  | Ujang | 100% |  | 100% |  | 100%
36 | OPM | PE | Operation | Master | Interface | 1. Plant Resource 2. Activity 3. Component Class 4. Cost Analysis Code 5. UOM 6. Conversion 7. Organization Code | Y |  | Ujang | 100% |  | 100% |  | 100%
37 | OPM | PE | Routing | Master | Interface | Prerequisite item : 1. Operation 2. Organization Code *Note: Enable enforce step dependency | Y |  | Ujang | 100% |  | 100% |  | 100%
38 | OPM | PD | Formula | Master | Interface | 1. Item Code 2. UOM 3. Organization Code | Y |  | Santi | 100% |  | 100% |  | 100%
39 | OPM | PE | Recipe | Master | Interface | 1. Formula 2. Routing 3. Organization Code | Y |  | Rina | 100% |  | 100% |  | 100%
41 | OPM | QC | Test Class | Master | Manual |  | Y |  | Rina | 100% |  | 100% |  | 100%
42 | OPM | QC | Test Method | Master | Manual |  | Y |  | Rina | 100% |  | 100% |  | 100%
43 | OPM | QC | Test Unit | Master | Manual |  | Y |  | Rina | 100% |  | 100% |  | 100%
44 | OPM | QC | Sampling Plan | Master | Manual |  | Y |  | Rina | 100% |  | 100% |  | 100%
45 | OPM | QC | Tests | Master | Interface | 1. Test Class 2. Test Method 3. Test Unit | Y |  | Rina | 100% |  | 100% |  | 100%
46 | OPM | QC | Tests Value | Master | Interface | 1. Test Class 2. Test Method 3. Test Unit | Y |  | Rina | 100% |  | 100% |  | 100%
47 | OPM | QC | Spec. Header | Master | Interface | 1. Item code 2. Organization Code | Y |  | Rina | 100% |  | 100% |  | 100%
48 | OPM | QC | Spec. Line | Master | Interface | 1. Specification Header 2. Tests | Y |  | Rina | 100% |  | 100% |  | 100%
49 | OPM | QC | Specification Validity Rule | Master | Interface | 1. Specification Header 2. Organization Code 3. Sampling Plan 4. Supplier 5. Recipe 6. Material Status | Y |  | Rina | 100% |  | 100% |  | 100%
50 | OPM | ASCP | Planning Sourcing Rule and Assignment Set | Master | Manual | 1. Item code 2. Organization Code 3. Sourcing Rule 4. Assignment Set | Data Loader |  | Nia | 100% |  | 100% |  | 100%
51 | OPM | ASCP | Safety Stock User Defined | Master | Manual | 1. Item code 2. Organization Code | Data Loader |  | Nia | 100% |  | 100% |  | 100%
91 | OTC | AR | Customer |  | Interface | 1. GL Account, LE 2. Profile Class 3. Payment Term 4. Sales person 5. Sales channel | Y |  | Pipit | 100% |  | 100% |  | 100%
92 | OTC | OM | Pricelist |  | Manual | 1. Item master 2. Item category 3. Customer | Y |  | Pipit | 100% |  | 100% |  | 100%
96 | OTC | AR | Approval Limit |  | Manual |  | Y |  | Lusi | 100% |  | 100% |  | 100%
99 | Finance | GL | CoA ORACLE |  | Dataload |  |  |  | Novi | 100% |  | 100% |  | 100%
100 | Finance | GL | Journal Source |  | Manual |  |  |  | Novi | 100% |  | 100% |  | 100%
101 | Finance | GL | Journal Category |  | Manual |  |  |  | Novi | 100% |  | 100% |  | 100%
102 | Finance | GL | Type Currency |  | Manual |  |  |  | Novi | 100% |  | 100% |  | 100%
103 | Finance | GL | List Currency include Precision |  | Manual |  |  |  | Novi | 100% |  | 100% |  | 100%
104 | Finance | GL | Budget Account Assignment |  | Dataload |  |  |  | Novi | 100% |  | 100% |  | 100%
105 | Finance | GL | Security Rules |  | Manual |  |  |  | Novi | 100% |  | 100% |  | 100%
106 | Finance | CM | Bank (Internal - Supplier) |  | Manual |  |  |  | Silvi | 100% |  | 100% |  | 100%
107 | Finance | FA | Asset Category include method and life years |  | Manual |  |  |  | Novi | 100% |  | 100% |  | 100%
108 | Finance | FA | Asset Key |  | Dataload |  |  |  | Novi | 100% |  | 100% |  | 100%
109 | Finance | FA | Location |  | Dataload |  |  |  | Novi | 100% |  | 100% |  | 100%
110 | Finance | FA | Retirement Type |  | Dataload |  |  |  | Novi | 100% |  | 100% |  | 100%
111 | Finance | GL | Hirarki dan Limit Journal Approval |  |  | 1. Asset Routes |  |  | Novi | 100% |  | 100% |  | 100%
112 | OTC |  | MASTER SHIPPING GRANT | [5 empty] | TITIN | 100% |  | 100% |  | 100%
113 | OTC |  | MASTER ROUTE | [5 empty] | TITIN | 100% |  | 100% |  | 100%
114 | OTC |  | MASTER RFID | [5 empty] | TITIN | 100% |  | 100% |  | 100%
115 | OTC |  | MASTER RATE |  |  |  |  | konfirmasi dari bu titin | TITIN | 100% |  | 100% |  | 95%
Note on D38: mohammad farouq: jangan lupa cost allocationnya

## Area
Stream | Stream Code | Module | Description
Finance | FIN | GL | General Ledger
|  | FA | Fixed Asset
|  | CE | Cash Management
Order To Cash | OTC | OM | Order Management
|  | AR | Receivable
Procure To Pay & WMS | PTP | PO | Purchasing
|  | INV | Inventory
|  | AP | Payable
|  | WMS | Warehouse Management System
Manufacturing | MFG | ASCP | ASCP Unconstrain
|  | PS | Production Scheduling
|  | PD | Product Develoment
|  | PE | Production Execution
|  | QC | Quality Control
|  | CM | Cost Management
Plant Maintenance | EAM | BOM | Bill of Material
|  | WIP | Work In Process
|  | EAM | Enterprise Asset Management
BI & Technical | BIT | BI | Business Intelligent
|  | DEV | Developer
100%
100%
100%
80%
|  |  |  | 2012-05-25 | 90%
30%
|  |  |  | 2012-05-25 | 100%
|  |  |  | 2012-05-25 | 100%
|  |  |  | 2012-05-25 | 100%
|  |  |  | 2012-05-25 | 100%

## Definition (hidden)
COLUMN | CODE | DESCRIPTION
Area | EBS | Oracle E-Business Suite
Module | ODM | Oracle Discrete Manufacturing
Data Element | BOM | Bill Of Material: list komponen dari tiap FG beserta koefisien dan satuannya
Data Element | ROUTING | List workcenter yg dilalui dari tiap FG mulai dari RM beserta resources yg digunakan (mesin, orang, listrik, air)
Data Element | QC | Jenis pekerjaan yang di QC beserta parameternya
Type | Master
Type | Balance
Template Readiness | Done | Data template is ready and given to user
Data Owner | INKO
Data Owner | PALINGDA
Data Owner | PAKO
Data Preparation - Status | In Progress | Data is being prepared according to template
Data Preparation - Status | Done | Data is already prepared according to template
Data Preparation - Status | Cancelled | Data is not necessary needed
Loading Tool Development - Load Method | Oraxcel
Loading Tool Development - Load Method | Data Loader
Loadting Tool Development - Status | In Progress | Tool is being developed
Loadting Tool Development - Status | Done | Tool is already developed and tested
Uploading Process | Uploading | Data is being uploaded
Uploading Process | Verifying | Uploaded data is being verified by user
Uploading Process | Done | Data is already uploaded and verified by user
Validation Process | In Progress | Data is being validated by user before uploaded
Validation Process | Done | Data is already valid and ready to be uploaded

## Sample (hidden)
[6 empty] | Data Preparation |  |  |  |  | Loading Tools Development |  |  |  |  | Load Testing
No | Area | Module | Data Element | Type | Template Readiness | Data Owner | PIC | Target Date | Actual Date | Status | Load Method | Tools Readiness | PIC | Status | Target date | PIC | Target date | Duration | Status
1 | EBS | PUR | Buyer | Master | Done | Henry Gunawan | Silvany |  |  | Done | Dataload |  |  | Manual
2 | All |  | Employee GG Marketing | Master | Done | Hokiono | Hokiono |  |  | Done | EIM |  | Lamsar | Manual
3 | All |  | Employee SM Marketing | Master | Done | Dzulkifli Syahril | Dzulkifli Syahril |  |  | Done | EIM |  | Lamsar | Manual
4 | EBS | PUR | Employee GG Procurement | Master | Done | Henry Gunawan | Silvany |  |  | Done | Dataload |  |  | Manual
5 | EBS | PUR | Employee GG Inventory | Master | Done | Henry Gunawan | Tantra |  |  | Done | Dataload |  |  | Manual
6 | EBS | PUR | Employee SM Inventory | Master | Done | Henry Gunawan | Yanna |  |  | Done | Dataload |  |  | Manual
7 | EBS | INV | Location GG | Master | Done | Henry Gunawan | Tantra |  |  | Done | Dataload |  |  | Manual
8 | EBS | INV | Location SM | Master | Done | Henry Gunawan | Yanna |  |  | Done | Dataload |  |  | Manual
9 | EBS | INV | Item Master Stock Merhandise | Master | Done | Henry Gunawan | Tantra |  |  | Done | Oraexel |  |  | Manual
10 | EBS | INV | Item Master Non Stock (Non Merchandise) | Master | Done | Hokiono | Tantra |  |  | Done | Oraexel |  |  | Manual
11 | EBS | INV | Item Master SM (Non Procurement GG) | Master | Done | Henry Gunawan | Yanna / Joni |  |  | Optional | Oraexel |  |  | Manual
12 | EBS | AP | Supplier Merchandise | Master | Done | Henry Gunawan | Silvany |  |  | Done | Oraexel |  |  | Manual
13 | EBS | AP | Supplier Non Merchandise (Event, Media, Brand, Research, Corporate, Outdoor) | Master | Done | Hokiono | Hokiono |  |  | Done | Oraexel |  |  | Manual
14 | EBS | PUR | Components Outdoor Item | Master | Done | Hokiono | Piaw |  |  | Done | Dataload |  |  | Manual
15 | EBS | GL | Account | Master | Done | Lusia | Lusia |  |  | Done | Dataload |  |  | Manual
16 | Siebel | EVENT | Venue | Master | Done | Hokiono | Ferry |  | 2011-05-19 | Done | EIM | 2011-03-22 | Lamsar | Done | 2011-03-23 | Lamsar | 2011-05-31 |  | Done
[11 empty] | STORE PROCEDURE | 1900-04-12 | Lamsar | Done | 1900-04-13 | Lamsar | 2011-05-31 |  | Done
17 | Siebel | EVENT | Event Goal Template | Master | Done | Hokiono | Ferry |  |  | Done | EIM | 2011-03-21 | Lamsar | Done | 2011-03-22 | Lamsar | 2011-03-22 |  | Done
[11 empty] | STORE PROCEDURE | 2011-04-18 | Lamsar | Done | 2011-04-18 | Lamsar | 2011-03-22 |  | Done
18 | Siebel | MRM | Activity Plan Template | Master | Done | Hokiono | Ferry |  |  | Done | EIM | 2011-03-21 | Lamsar | Done | 2011-03-23 | Lamsar | 2011-03-23 |  | Done
[11 empty] | STORE PROCEDURE | 2011-04-19 | Lamsar | Done | 2011-04-19 | Lamsar | 2011-03-23 |  | Done
19 | Siebel | MRM | LOV KPI Metrics Event | Master | Done | Hokiono | Ferry |  |  | Done | Manual |  |  | Manual
20 | Siebel | MRM | LOV Event Category | Master | Done | Hokiono | Ferry |  |  | Done | Manual |  |  | Manual
21 | Siebel | MRM | LOV Event Type | Master | Done | Hokiono | Ferry |  |  | Done | Manual |  |  | Manual
22 | Siebel | MRM | LOV Activity Type | Master | Done | Hokiono | Ferry |  |  | Done | Manual |  |  | Manual
23 | Siebel | MRM | LOV Event Status | Master | Done | Hokiono | Ferry |  |  | Done | Manual |  |  | Manual
24 | Siebel | MRM | LOV PR Type - Event | Master | Done | Hokiono | Ferry |  | 2011-03-08 | Done | Manual |  |  | Manual
25 | Siebel | MRM | LOV PR Verification Status - Event | Master | Done | Hokiono | Ferry |  | 2011-03-08 | Done | Manual |  |  | Manual
26 | Siebel | MRM | Brand | Master | Done | Hokiono | Agus L |  |  | Done | Manual |  |  | Manual
27 | Siebel | MRM | Period | Master | Done | Hokiono |  |  |  | Done | Manual |  |  | Manual
28 | Siebel | MRM | COA Marketing | Master | Done | Hokiono | Chandra |  |  | Done | EIM | 2011-03-22 | Lamsar | Done | 2011-03-31 | Lamsar | 2011-06-03 |  | Done
[11 empty] | STORE PROCEDURE | 2011-04-13 | Lamsar | Done | 2011-04-14 | Lamsar | 2011-06-03 |  | Done
29 | Siebel | MRM | Location (Fund) | Master | Done | Dzulkifli Syahril | Dzulkifli Syahril |  |  | Done | EIM | 2011-03-22 | Lamsar | Done | 2011-03-24 | Lamsar | 2011-05-31 |  | Done
[11 empty] | STORE PROCEDURE | 2011-04-15 | Lamsar | Done | 2011-04-15 | Lamsar | 2011-05-31 |  | Done
30 | Siebel | MRM | Initiatives Goal Template | Master | Done | Hokiono | Chandra |  |  | Optional | EIM | 2011-03-23 | Lamsar | Done | 2011-03-25
31 | Siebel | MRM | Program Goal Template | Master | Done | Hokiono | Chandra |  |  | Optional | EIM | 2011-03-23 | Lamsar | Done | 2011-03-28
32 | Siebel | MRM | LOV Initiative Type | Master | Done | Hokiono | Chandra |  | 2011-03-08 | Done | Manual |  |  | Manual
33 | Siebel | MRM | LOV Initiative Status | Master | Done | Hokiono | Chandra |  | 2011-03-08 | Done | Manual |  |  | Manual
34 | Siebel | MRM | LOV Initiative Approval Status | Master | Done | Hokiono | Chandra |  | 2011-03-08 | Done | Manual |  |  | Manual
35 | Siebel | MRM | LOV Notes Type | Master | Done | Hokiono | Chandra |  |  | Cancelled | Manual |  |  | Manual
36 | Siebel | MRM | LOV Channel | Master | Done | Hokiono | Chandra |  | 2011-03-08 | Done | Manual |  |  | Manual
37 | Siebel | MRM | LOV Program Type | Master | Done | Hokiono | Chandra |  |  | Done | Manual |  |  | Manual
38 | Siebel | MRM | LOV Program Category | Master | Done | Hokiono | Chandra |  |  | Done | Manual |  |  | Manual
39 | Siebel | MRM | LOV Program Status | Master | Done | Hokiono | Chandra |  | 2011-03-08 | Done | Manual |  |  | Manual
40 | Siebel | MRM | LOV Program Approval Status | Master | Done | Hokiono | Chandra |  | 2011-03-08 | Done | Manual |  |  | Manual
41 | Siebel | MRM | LOV Target Type | Master | Done | Hokiono | Chandra |  | 2011-03-08 | Done | Manual |  |  | Manual
42 | Siebel | MRM | LOV KPI Metrics Brand | Master | Done | Hokiono | Chandra |  |  | Done | Manual |  |  | Manual
43 | Siebel | MRM | LOV Payment Allocation | Master | Done | Hokiono | Chandra |  | 2011-03-08 | Done | Manual |  |  | Manual
44 | Siebel | MRM | LOV PR Type - Brand | Master | Done | Hokiono | Chandra |  | 2011-03-08 | Done | Manual |  |  | Manual
45 | Siebel | MRM | LOV PR Verification Status - Brand | Master | Done | Hokiono | Chandra |  | 2011-03-08 | Done | Manual |  |  | Manual
46 | Siebel | ASSETS | Marketing Assets Group Location | Master | Done | Hokiono | Piaw |  | 2011-05-10 | Done | EIM | 2011-04-06 | Lamsar | Done | 2011-04-07 | Lamsar | 2011-06-01 |  | Done
47 | Siebel | MRM | Approval Hierarchy (Approval Admin) | Master | Done | Hokiono | Chandra |  |  | Done | EIM |  | Lamsar | Done |  | Lamsar | 2011-06-01 |  | Done
48 | Siebel | MRM | Organization Hierarchy | Master | Done | Hokiono | Chandra |  |  | Done | Manual
49 | Siebel | MRM | Position Hierarchy | Master | Done | Hokiono | Chandra |  |  | Done | Manual
50 | Siebel | ASSETS | Marketing Assets | Balance | Done | Hokiono | Piaw |  | 2011-05-10 | Done | EIM |  | Lamsar | Done | 2011-04-26 | Lamsar | 2011-06-01 |  | Done
51 | Siebel | ASSETS | Marketing Assets Detail | Balance | Done | Hokiono | Piaw |  | 2011-05-10 | Done | EIM |  | Lamsar |  |  | Lamsar | 2011-06-01 |  | Done
52 | Siebel | MRM | Marketing Initiatives | Balance | Done | Hokiono | Agus L |  | 2011-05-25 | Done | EIM | 2011-03-25 | Lamsar | Done | 2011-03-25 | Lamsar | 2011-06-06 |  | Done
[11 empty] | STORE PROCEDURE | 2011-04-22 | Lamsar | Done | 2011-04-21 | Lamsar | 2011-06-06 |  | Done
53 | Siebel | MRM | Marketing Plan GG | Balance | Done | Hokiono | Agus L |  | 2011-05-25 | Done | EIM | 2011-03-29 | Lamsar | Done | 2011-03-29 | Lamsar | 2011-06-08 |  | Done
[11 empty] | STORE PROCEDURE | 2011-04-26 | Lamsar | Done | 2011-04-26 | Lamsar | 2011-06-08 |  | Done
54 | Siebel | MRM | Marketing Fund GG | Balance | Done | Hokiono | Agus L |  | 2011-05-25 | Done | EIM | 2011-03-31 | Lamsar | Done | 2011-03-31 | Lamsar | 2011-06-08 |  | Done
[11 empty] | STORE PROCEDURE | 2011-04-27 | Lamsar | Done | 2011-04-27 | Lamsar | 2011-06-08 |  | Done
55 | Siebel | MRM | Programs GG | Balance | Done | Hokiono | Agus L |  | 2011-05-26 | Done | EIM | 2011-03-30 | Lamsar | Done | 2011-03-30 | Lamsar | 2011-06-09 |  | Done
[11 empty] | STORE PROCEDURE | 2011-05-02 | Lamsar | Done | 2011-04-28 | Lamsar | 2011-06-09 |  | Done
56 | Siebel | MRM | Budget Requests GG | Balance | Done | Hokiono | Agus L |  | 2011-05-26 | Done | EIM | 2011-03-31 | Lamsar | Done | 2011-03-31 | Lamsar | 2011-06-10 |  | Done
57 | Siebel | MRM | Expenses GG | Balance | Done | Hokiono | Agus L |  |  | Cancelled | EIM | 2011-04-01 | Lamsar | Done | 2011-04-01
[11 empty] | STORE PROCEDURE | 2011-04-18 | Lamsar | Done | 2011-04-18
[11 empty] | SHELL SCRIPT | 2011-04-18 | Lamsar | Done | 2011-04-18
58 | Siebel | MRM | Marketing Plan SM | Balance | Done | Agung P | Dzulkifli Syahril |  |  | 50 | EIM | 2011-03-29 | Lamsar | Done | 2011-03-29 | Lamsar | 2011-06-08 |  | Done
59 | Siebel | MRM | Marketing Fund SM | Balance | Done | Agung P | Dzulkifli Syahril |  |  | 50 | EIM | 2011-03-31 | Lamsar | Done | 2011-03-31 | Lamsar | 2011-06-08 |  | Done
60 | Siebel | MRM | Programs SM | Balance | Done | Agung P | Dzulkifli Syahril |  |  | 50 | EIM | 2011-03-30 | Lamsar | Done | 2011-03-30 | Lamsar | 2011-06-09 |  | Done
61 | Siebel | MRM | Budget Requests SM | Balance | Done | Agung P | Dzulkifli Syahril |  |  | 50 | EIM | 2011-03-31 | Lamsar | Done | 2011-03-31 | Lamsar | 2011-06-10 |  | Done
62 | Siebel | MRM | Expenses SM | Balance | Done |  |  |  |  | Cancelled | EIM | 2011-04-01 | Lamsar | Done | 2011-04-01
[11 empty] | STORE PROCEDURE | 2011-04-18 | Lamsar | Done | 2011-04-18
[11 empty] | SHELL SCRIPT | 2011-04-18 | Lamsar | Done | 2011-04-18
63 | EBS | INV | Marketing Inventory Stock GG | Balance | Done | Henry Gunawan | Tantra |  |  | 0 | Oraexel |  |  | Manual
64 | EBS | INV | Marketing Inventory Stock SM | Balance | Done | Henry Gunawan | Yanna |  |  | 0 | Oraexel |  |  | Manual
65 | EBS | AP | Tax Codes (WHT Tax) | Master | Done | Agus L | Agus L |  |  | Done | Dataload |  |  | Manual
66 | Siebel | PR | Purchase Requisition Merhandise | Balance | Done | Henry Gunawan | Silvany |  |  | Cancelled | EIM |  | Lamsar | Done | 2011-05-05
67 | EBS | PUR | Purchase Order Merhandise | Balance | Done | Henry Gunawan | Silvany |  |  | Cancelled | Oraexel | 2011-04-29 | Satria | Done
68 | EBS | PUR | Receiving Merhandise | Balance | Done | Henry Gunawan | Silvany |  |  | Cancelled | Oraexel | 2011-04-29 | Satria | Done
69 | EBS | AP | Invoice Merhandise | Balance | Done | Henry Gunawan | Silvany |  |  | Cancelled | Oraexel | 2011-04-29 | Satria | Done
70 | EBS | AP | Payment Merhandise | Balance | Done | Henry Gunawan | Silvany |  |  | Cancelled | Oraexel | 2011-04-29 | Satria | Done
71 | Siebel | PR | Purchase Requisition Non Merhandise (Event, Media, Brand, Research, Corporate, Outdoor) | Balance | Done | Hokiono | Agus L |  |  | Cancelled | EIM |  | Lamsar
72 | EBS | PUR | Purchase Order Non Merhandise (Event, Media, Brand, Research, Corporate, Outdoor) | Balance | Done | Hokiono | Agus L |  |  | Cancelled | Oraexel | 2011-04-29 | Satria | Done
73 | EBS | PUR | Receiving Non Merhandise (Event, Media, Brand, Research, Corporate, Outdoor) | Balance | Done | Hokiono | Agus L |  |  | Cancelled | Oraexel | 2011-04-29 | Satria | Done
74 | EBS | AP | Invoice Non Merhandise (Event, Media, Brand, Research, Corporate, Outdoor) | Balance | Done | Hokiono | Agus L |  |  | Cancelled | Oraexel | 2011-04-29 | Satria | Done
75 | EBS | AP | Payment Non Merhandise (Event, Media, Brand, Research, Corporate, Outdoor) | Balance | Done | Hokiono | Agus L |  |  | Cancelled | Oraexel | 2011-04-29 | Satria | Done
76 | EBS | PO | Hierarchy Approval PO (All Type - Merhandise, Outdoor, Media, Event, Corporate, Research) | Master | Done | Henry Gunawan | Silvany |  |  | Cancelled
77 | Siebel | MRM | Responsibility View | Master | Done |  |  |  |  | Done | EIM |  | Lamsar | Done | 2011-05-11
79 | Siebel | MRM | Validation Messages | Master | Done |  |  |  |  | Done | EIM |  | Lamsar |  |  | Lamsar | 2011-06-01 |  | Done
80 | Siebel | MRM | Rules | Master | Done |  |  |  |  | Done | EIM |  | Lamsar | Done |  | Lamsar | 2011-06-01 |  | Done
81 | EBS | PUR | Outstanding Purchase Order Non Termin | Balance | Done | Henry Gunawan | Silvany |  |  | 50 | Oraexel | 2011-06-05 | Satria | Done |  | Wendo | 2011-06-02 |  | Done

## Upload Schedule (hidden)
Dataload
Interface
Manual
Actual upload
Invidual Upload Master Data
[8 empty] | CRP 2 (Upload) |  |  |  | Dependent Master Data
Seg | Stream | Module | Data Name | Type | Upload Method | PIC MII | Template | Target Date | Actual Date | Status (%) |  | Dependency Remarks | 28 | 29 | 30 | 31 | 1 | Sab | MG | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | Backup (11 jan 12 , 10.16 PM) | Remarks
1 | PTP | PO | Job | Master | Manual | Anndy | Y
2 | PTP | PO | Position | Master | Manual | Anndy | Y
3 | PTP | PO | Personnel/Employee (PO, WMS) | Master | Manual | Anndy | Y | [21 empty] | belum termasuk employee untuk eam
4 | PTP | PO | Position Hierarchy (approval path) | Master | Manual | Anndy | Y
5 | PTP | PO | Approval Group & Approval Assignment | Master | Manual | Anndy | Y
6 | PTP | AP | Payment Terms | Master | Manual | Anndy | Y
7 | PTP | AP | Suppliers (Internal & External) | Master | Interface | Anndy | Y
8 | PTP | AP | Withholding Tax | Master | Manual | Anndy | Y
9 | PTP | AP | Document Sequence (AP Invoice & Payment) | Master | Manual | Anndy | Y
10 | WMS | INV | Unit of Measures | Master | Data loader | Tabrani | Y
11 | WMS | INV | Item UOM Conversion | Master | Data loader | Tabrani | Y |  |  |  |  | WMS (10)
12 | WMS | INV | Item Template | Master | Manual | Tabrani | N
13 | WMS | INV | Subinventory & Locator | Master | Manual | Tabrani | N
14 | WMS | INV | Item Category - Purchasing Categories | Master | Data loader | Tabrani | Y
15 | WMS | INV | Item Category - Price Class | Master | Data loader | Tabrani | Y
16 | WMS | INV | Item Category - Product Hierarchy | Master | Data loader | Tabrani | Y
17 | WMS | INV | Item Category - Cost Component Class | Master | Data loader | Tabrani | Y
18 | WMS | INV | Item Category - GL Class | Master | Data loader | Tabrani | Y
19 | WMS | INV | Item Category - WMS | Master | Data loader | Tabrani | Y
20 | WMS | INV | Item Category - Sequence Dependancy Class | Master | Data loader | Tabrani | Y
21 | WMS | INV | Item Category - Planning Category | Master | Data loader | Tabrani | Y
22 | WMS | INV | Item Master - Raw & Packaging Material | Master | Interface | Tabrani | Y |  |  |  |  | WMS (10,12)
23 | WMS | INV | Item Master - Finished Good | Master | Interface | Tabrani | Y |  |  |  |  | WMS (10,12), OTC (96)
24 | WMS | INV | Item Master - Finished Good Export | Master | Interface | Tabrani | Y |  |  |  |  | WMS (10,12),OTC (96)
25 | WMS | INV | Item Master - Finished Good Toll In | Master | Interface | Tabrani | Y |  |  |  |  | WMS (10,12), OTC (96)
26 | WMS | INV | Item Master - Trading | Master | Interface | Tabrani | Y |  |  |  |  | WMS (10,12)
27 | WMS | INV | Item Master - Work In Process | Master | Interface | Tabrani | Y |  |  |  |  | WMS (10,12)
28 | WMS | INV | Item Master - Sparepart | Master | Interface | Tabrani | Y |  |  |  |  | WMS (10,12)
29 | WMS | INV | Item Master - Project | Master | Interface | Tabrani | Y |  |  |  |  | WMS (10,12) | [16 empty] | No need CRP3
30 | WMS | INV | Item Master - Raw Material Toll In | Master | Interface | Tabrani | Y |  |  |  |  | WMS (10,12)
31 | WMS | INV | Item Master - Marketing | Master | Interface | Tabrani | Y |  |  |  |  | WMS (10,12)
32 | WMS | INV | Item Master - Expense | Master | Interface | Tabrani | Y |  |  |  |  | WMS (10,12)
33 | WMS | INV | Item Master - Asset | Master | Interface | Tabrani | Y |  |  |  |  | WMS (10,12)
34 | WMS | INV | Item Master - Reworks | Master | Interface | Tabrani | Y |  |  |  |  | WMS (10,12)
35 | NA | NA | NA | NA | NA | NA
36 | NA | NA | NA | NA | NA | NA
37 | OPM | CM | Cost Component Class | Master | Manual | Bagus | Y
38 | OPM | CM | Cost Analysis Code | Master | Manual | Bagus | Y
39 | OPM | PE | Resource Class | Master | Manual | Yudi | Y
40 | OPM | PE | Generic Resource | Master | Interface | Yudi | Y |  |  |  |  | OPM (37,39)
41 | OPM | PE | Plant Resource | Master | Interface | Yudi | Y |  |  |  |  | OPM (40), EAM (Equipment Item), INV (Calendar), WMS (10)
42 | OPM | PE | Activity | Master | Manual | Yudi | Y
43 | OPM | PE | Operation | Master | Interface | Yudi | Y |  |  |  |  | OPM (41,42,37) , WMS (10) , WMS Organization Code
44 | OPM | PE | Routing | Master | Interface | Yudi | Y |  |  |  |  | OPM (43) , WMS Organization Code
45 | OPM | PD | Formula | Master | Interface | Yudi | Y |  |  |  |  | WMS Organization Item, WMS (10) , WMS Organization Code
46 | OPM | PE | Recipe | Master | Interface | Yudi | Y |  |  |  |  | OPM (44,45) WMS Organization Code
47 | OPM | PE | Step/Material Association Setup | Master | Interface | Yudi | [5 empty] | OPM (46,43), WMS Organization Item
48 | OPM | QC | Test Class | Master | Manual | Bagus | Y
49 | OPM | QC | Test Method | Master | Manual | Bagus | Y
50 | OPM | QC | Test Unit | Master | Manual | Bagus | Y
51 | OPM | QC | Sampling Plan | Master | Manual | Bagus | Y |  |  |  |  | WMS (11)
52 | OPM | QC | Tests | Master | Interface | Bagus | Y |  |  |  |  | OPM (48.49,50)
53 | OPM | QC | Tests Value | Master | Interface | Bagus | Y |  |  |  |  | OPM (52)
54 | OPM | QC | Spec. Header | Master | Interface | Bagus | Y |  |  |  |  | WMS (22,23,24,25,27,30,34) Organization Item, Organization Code
55 | OPM | QC | Spec. Line | Master | Interface | Bagus | Y |  |  |  |  | OPM (52,54)
56 | OPM | QC | Specification Validity Rule | Master | Interface | Bagus | Y |  |  |  |  | OPM (54) WMS Material Status , Organzation Code,,OPM (51) OPM(55,43,44,45,46),WMS (22,23,24,25,27,30,34) AP (7,)
57 | OPM | PS | Sequence Dependent Setup | Master | Manual | Yudi | Y |  |  |  |  | WMS Organization Item, OPM (43, WMS Item Category: Sequence Dependency Class, WMS Organization Code
58 | EAM | EAM | Area | Master | Manual | Andi Thamrin | Y
59 | EAM | EAM | Resource-Internal | Master | Manual | Andi Thamrin | Y |  |  |  |  | PTP (3)
60 | EAM | EAM | Resource-External |  | Manual | Andi Thamrin | Y
61 | EAM | EAM | Owning Department |  | Manual | Andi Thamrin | Y |  |  |  |  | EAM (59)
62 | EAM | EAM | Department |  | Manual | Andi Thamrin | Y |  |  |  |  | EAM (59)
63 | EAM | EAM | Department Approver |  | Manual | Andi Thamrin | Y |  |  |  |  | EAM (62)
64 | EAM | EAM | Activity Type |  | Manual | Andi Thamrin | Y
65 | EAM | EAM | Activity Cause |  | Manual | Andi Thamrin | Y
66 | EAM | EAM | Activity Source |  | Manual | Andi Thamrin | Y
67 | EAM | EAM | Priority |  | Manual | Andi Thamrin | Y
68 | EAM | EAM | Criticality |  | Manual | Andi Thamrin | Y
69 | EAM | EAM | Work Request Type |  | Manual | Andi Thamrin | Y
70 | EAM | EAM | Work Order Reconciliation Code |  | Manual | Andi Thamrin | Y
71 | EAM | EAM | Work Order Type |  | Manual | Andi Thamrin | Y
72 | EAM | EAM | Asset Category |  | Dataload | Andi Thamrin | Y
73 | EAM | EAM | Asset Group |  | Interface | Andi Thamrin | Y
74 | EAM | EAM | Asset Group-Category |  | Interface | Andi Thamrin | Y |  |  |  |  | EAM (72,73)
75 | EAM | EAM | Asset BOM |  | Interface | Andi Thamrin | Y |  |  |  |  | EAM (73), WMS (28)
76 | EAM | EAM | Activity-Asset |  | Interface | Andi Thamrin | Y
77 | EAM | EAM | Maintenance Routing |  | Interface | Andi Thamrin | Y |  |  |  |  | EAM (62,76)
78 | EAM | EAM | Maintenance BOM |  | Interface | Andi Thamrin | Y |  |  |  |  | EAM (76), WMS (28)
79 | EAM | EAM | Rebuildable Category |  | Dataload | Andi Thamrin | Y | [21 empty] | Tidak menggunakan rebuildable Category
80 | EAM | EAM | Rebuildable Item |  | Interface | Andi Thamrin | Y
81 | EAM | EAM | Rebuildable BOM |  | Interface | Andi Thamrin | Y |  |  |  |  | EAM (80), WMS (28) | [16 empty] | Tidak menggunakan rebuildable BOM
82 | EAM | EAM | Activity Association Template1 |  | Interface | Andi Thamrin | Y |  |  |  |  | EAM (73,76)
83 | EAM | EAM | Meter Template |  | Interface | Andi Thamrin | Y
84 | EAM | EAM | Meter Template Association |  | Interface | Andi Thamrin | Y |  |  |  |  | EAM (73,83)
85 | EAM | EAM | Schedule Template Definition |  | Interface | Andi Thamrin | Y |  |  |  |  | EAM (73,82,84)
86 | EAM | EAM | Suppression |  | Interface | Andi Thamrin | Y |  |  |  |  | EAM (73,82)
87 | EAM | EAM | Last Service Info |  | Interface | Andi Thamrin | Y |  |  |  |  | EAM (88) | [16 empty] | Testing CRP3 menggunakan dummy data
88 | EAM | EAM | Asset Number |  | Interface | Andi Thamrin | Y |  |  |  |  | EAM (58,61,67,68,73,82,84,85,92,123,124) | [16 empty] | 1400 record , 80%
89 | EAM | EAM | Asset Attribute |  | Interface | Andi Thamrin | Y |  |  |  |  | EAM (88)
90 | EAM | EAM | Rebuildable Number |  | Interface | Andi Thamrin | Y |  |  |  |  | EAM (58,61,67,68,80,82,84,85,92)
91 | EAM | EAM | Rebuildable Attribute |  | Interface | Andi Thamrin | Y |  |  |  |  | EAM (90) | [16 empty] | Use dummy
92 | EAM | EAM | WIP Acc Class |  | Manual | Andi Thamrin | Y |  |  |  |  | Finance (107)
93 | EAM | EAM | Failure Analysis |  | Interface | Andi Thamrin | Y |  |  |  |  | EAM (73)
94 | EAM | EAM | Asset Routes |  | Interface | Andi Thamrin | [5 empty] | EAM (88) | [16 empty] | Duplicate data tidak diupload, 90%
95 | EAM | EAM | Min Max Item Sparepart |  | Interface | Andi Thamrin | Y |  |  |  |  | WMS (28)
96 | OTC | OM | Item Price Class dan Hirarki Item |  | Interface | Melissa | [22 empty] | Consider untuk di maintain di Inv
97 | OTC | AR | Customer |  | Interface | Devia | [5 empty] | OTC (98,100,Finance (107) | [16 empty] | Sales office dan distributor, yang belum export
98 | OTC | OM | Pricelist |  | Manual | Melissa | [5 empty] | WMS (23,24,25,26)
99 | OTC | OM | Discount |  | Manual | Melissa | [5 empty] | WMS (23,24,25,26)
100 | OTC | OM | Order Type |  | Manual | Melissa | [5 empty] | OTC (102)
101 | OTC | OM, AR, INV | Transaction Numbering |  | Manual | Devia
102 | OTC | AR | Transaction Type (AR) |  | Manual | Devia | [5 empty] | Finance (107)
103 | OTC | AR | Payment term |  | Manual | Devia
104 | OTC | AR | Approval Limit |  | Manual | Devia | [22 empty] | waiting user id
105 | OTC | AR | Receipt Method |  | Manual | Devia | [5 empty] | Finance (117
106 | OTC | AR | Receivables Activity |  | Manual | Devia | [5 empty] | Finance (107)
107 | Finance | GL | CoA Namasindo Plas |  | Dataload | Ferryzal
108 | Finance | GL | CoA Mapping SAFE |  | Dataload | NA | [5 empty] | Tidak di upload , Maintain manual diluar oracle | [16 empty] | Maintain Manual excel
109 | Finance | GL | CoA Consolidation (Mapping Parent-Subsidiary) |  | Dataload | NA
110 | Finance | GL | Journal Source – Include SAFE |  | Manual | Lionnie
111 | Finance | GL | Journal Category – Include SAFE |  | Manual | Lionnie
112 | Finance | GL | Type Currency |  | Manual | Lionnie
113 | Finance | GL | List Currency include Precision |  | Manual | Lionnie
114 | Finance | GL | Budget Account Assignment |  | Dataload | Lionnie
115 | Finance | GL | Cross Validation Rules |  | Manual | Lionnie | [5 empty] | Finance (107)
116 | Finance | GL | Security Rules |  | Manual | Lionnie | [5 empty] | Menunggu Security Matrix | [16 empty] | Waiting for security matrix
117 | Finance | CM | Bank (Internal & Supplier) |  | Manual | Ferryzal&Lionnie
118 | Finance | CM | Transaction Codes for Auto reconcile |  | Manual | Lionnie
119 | Finance | FA | Asset Category include method and life years |  | Manual | Lionnie
120 | Finance | FA | Asset Key |  | Dataload | Lionnie
121 | Finance | FA | Location |  | Dataload | Lionnie
122 | Finance | FA | Retirement Type |  | Dataload | Lionnie
123 | EAM | EAM | Equipment Item |  | Interface | Andi Thamrin
124 | Finance | FA | FA Number (Sample opbal FA) |  | Interface | Lionnie |  |  |  |  | `
| EAM | EAM | Asset Group-Asset attribute assignment |  | Dataload | Andi Thamrin